Whitecote Primary School

Whitecote Primary School Access Plan: 2023-2026

Whitecote Primary School Access Plan: 2023-2026

| Aim | Current Good Practice | Objectives | Actions | Person/s responsible | Date to be completed | Success criteria |
| --- | --- | --- | --- | --- | --- | --- |
| Ensure all pupils have access to the curriculum, expanding the curriculum as necessary to ensure pupils with a disability are as, equally prepared. | Our school offers a differentiated curriculum for all pupils We use resources tailored to the needs of pupils who require support to access the curriculum Teachers have been given information on how to adapt learning in their curriculum subject. Key ideas and strategies have been added to the subject schemes of work by subject leaders. Curriculum resources include examples of people with disabilities, eg books, toys, PSHE Ensure all pupils develop an awareness of disability and disabled pupils in school. Curriculum progress is tracked for all pupils using PixL and B Squared is used for children who have a special educational need. The Autism Progression Framework is used to track the progress for children with ASD. Targets are set effectively and are appropriate for pupils with additional needs, using Individual Provision Maps and EHCPs. The curriculum is reviewed to ensure it meets the needs of all pupils Training/dissemination of information to staff as appropriate. School supports and actively encourages all pupils in partnership with parents to take part in schools and residential visits and other school experiences. Children with a disability have a Risk Assessment and a PEEP for residential and school visits. |  |  | All staff All staff All staff All staff Subject leaders Class teachers SENDCO/Assistant SENDCo Class teachers supported by the SENDCo and Assistant SENDCo Headteacher, SLT and class teachers All staff All staff | Ongoing Ongoing Ongoing Ongoing Termly Termly Ongoing Ongoing Ongoing | Learning walks and book looks are evidence that all children are accessing a broad and balanced curriculum Resources are adapted for any child to ensure full accessibility to a learning experience Whole school assemblies and the PSHE curriculum offer opportunities for extended learning around disability Data for Pixl and B Squared are assessed termly Individual Provision Maps (IPMs) and the outcomes within them are reviewed termly to ensure progress and access Children with EHCPs have individual EHCP trackers that are reviewed termly. School staff regularly review the curriculum offer Class teachers have a thorough knowledge of their children’s needs All staff positively encourage participation in class and school activities with reasonable adjustments where required. |
| Provide suitable access to the physical environment of the school | The environment is adapted to the needs of pupils as required. This includes: Ramp access around the entire school site External LED lighting and under lighting around the school site Matt external school signage External site signage is clearly visible around the outside of the building and at all entrances and exits Ground floor level access to the school site Wide internal corridors Disabled parking bays on the school site Disabled toilets with changing facilities and separate Care Suite on the ground floor Library/book shelves at wheelchair-accessible height Flat path access to the school environment Edges of external steps into classrooms are painted yellow to be highly visible Classroom doors are wider for accessibility Carpets have been fitted to replace shiny surfaces to improve the environment for the visually impaired. External shelters from the elements are fully accessible Internal doors around school have exit buttons at an accessible height School office hatch at accessible height with information signage at lower levels Fire alarm – there are links to the Fire Risk assessment This is tested weekly The fire alarm flashes to alert those who are hard of hearing All fire doors automatically open in the event of a fire | Objective: Provide signage for visitors to signify where the school office is located Objective: To ensure all steps, ramps and low walls are highly visible for visually impaired. Objective: Provide a hearing loop for hearing impaired children, staff and visitors | Action: To display external signage on the wall where the footpath leads from the bottom gate to alert visitors to the School Office and Acorns class. Display similar signage at the main school gate to alert visitors to the school office and Acorns class. External noticeboards around the school grounds are updated and refreshed with communications and letters from school Action: To refresh all yellow paint around the school grounds to ensure they are highly visible Action: A new one-to-one system will be purchased Test for functionality | Superintendent Superintendent Superintendent Superintendent Superintendent SLT Superintendent Superintendent Superintendent Superintendent Superintendent Superintendent Headteacher Business Manager Superintendent | Ongoing End of the Autumn term 2023 Ongoing Ongoing Ongoing End of the Autumn term 2023 Ongoing Ongoing End of Autumn term 2023 | The external and internal school site will be fully accessible to all stakeholders February 2024 Yellow stripe will alert pedestrians to the uneven surface Edges of classroom steps will be bright yellow and highly visible The external site and the office reception will be fully accessible to visitors to the school School will be fully accessible to hearing impaired visitors and staff |
| Ensure suitable delivery of information to pupils with a disability and their families | Our school uses a range of communication methods to ensure information is accessible. This includes: Internal signage Large print resources Braille Induction loops Pictorial or symbolic representations Radio Aids Makaton and PECS Individual PEEPs and Individual Risk Assessments All teachers complete PEEPs and IPRAs for individuals who require them – documents updated and talked through with the children. Teachers upload these to CPOMS. | Objective: Enhance the accessibility for visually children, families and visitors Objective: To provide all children with a disability adapted information on how to evacuate the school in the event of a fire Objective: Ensure the school communications and accessibility to school information for families with English as an additional language or additional individual needs are in place | Actions: Provide letters in large font and establish the Braille offer of communication appropriate to a mainstream school Action: Provide pictorial Fire Evacuation plans for each classroom and display them at an accessible height Action: Provide text to speak function on individual devices for parents/carers to have texts read to them Enhance the school website to have an accessible translation functionality Provide letters for parents in English and in their home language | Office staff SENCo supported by CYC Specialist agencies Katie Buller Class teachers supported by the Pupil Well-being Manager, SENDCo or Assistant SENDCo Office staff Josh Saville-Gill | Ongoing February 2024 End of Autumn Term 2023 February 2024 | Children with a disability will receive the same information as their peers but with adjustments in place and modified to meet their individual access needs Additional support staff will be in place where appropriate to support children’s accessibility needs |